## Slide 1
Network Meeting
3rd February 2022

## Slide 2
Supervisory Board Agenda
3 February 2022
12.30 - 13.30 GMT / 13.30 - 14.30 CET
1. Updates from Vicky Walter, Project Manager
    i. Overview of CEN structure
    ii. CEN progress to date
    iii. Training and development
2. Research co-operation
3. Any other business
4. Date of next meeting

## Slide 3
1. Overview of CEN structure
Contracts/agreements
Consortium bodies
Role of Supervisory Board
2. CEN progress to date
Recruitment
Deliverables and milestones
Website
3. Training and development
Project Manager Update

## Slide 4
Grant Agreement (inc. Consortium Plan)
Consortium Agreement
Partner Agreements
Secondment Agreements
Material Transfer Agreement
Data Transfer Agreement
Advisory Board NDA
CEN Governance – contracts/agreements

## Slide 5
Academic Assembly
Supervisory Board
Funding Authority
Network Coordinator/
Project Manager
Work Package Leads
External Advisory Board
Ethics Advisory Board
Ethics Committee
Development Team
ESR Committee
CEN Governance – Consortium bodies

## Slide 6
Monitor project progress and implementation according to Consortium Plan
Assist with preparation of press releases and joint publications and meetings with Funding Authority
Help prepare for meetings with the Funding Authority and in preparing related data and deliverables
Oversee quality of supervision and training of ESRs and ensure balance between scientific and transferable skills
Role of the Supervisory Board
Terms of Reference – to be accepted at next meeting

## Slide 7
Recruitment
Call for applications
Criteria: mobility and career stage
Advertised: Euraxess, website, FENS, networks
Shortlisting
CEN selection criteria
Interviews
Presentations
Supervisors and co-supervisors, others from host
References
Call for applications
Additional criteria
Task
Recruitment round 1 and 2
Recruitment round 3
Shortlisting
Interviews
References

## Slide 8
Recruitment
Advertised 13 positions
Received 107 applications
Held 21 interviews
Recruited 8 ESRs
Round 1
Advertised 5 positions
Received 71 applications
Held 15 interviews
Recruited 4 ESRs
Round 2
Advertised 2 positions
Received 226 applications
Held 8 interviews
Recruited 2 ESRs
Round 3

## Slide 9
Julie Urrutia Desmaison
Ahsan Ayyaz
Gabriela Neubert da Silva
To be appointed
Camilla Ciapponi
Alice Doubliez
Dianela Osorio Becerra
Yuhe Li
Fernando Senovilla Sanz
Vasiliki Spatharioti
Tuğçe Yildiz
Enzo Nio
Jingjing Ye
Mahdie Ghane Ezabadi
Patricia Gil Paterna

## Slide 10
WP1 Management |  | WP2 ESR Development |  | WP3 Ethics |  | WP 4-7 Research Objectives |  | WP8 Dissemination | 
Supervisory Board reps | Jul 21 | Career Development Plan for each ESR | Jun 22 | Humans – informed consent | Oct 21 | Presentation at international conference | May 24 | Establish CEN identity (logo, templates etc.) | Jul 21
Consortium Agreement | Nov 21 | Joint review article by ESRs | Nov 22 | Data processing | Oct 21 | Develop manuscripts for submission | May 25 | Establish website | Aug 21
Advertisements of ESR posts | Aug 21 | Mini symposium proposal submitted to SFN 2022 | May 23 | Animals - authorisations | Sep 22 |  |  | Press releases for CEN | Jul 21
Data Manage-ment Plan | Nov 21 | Publication for a lay readership | May 23 | Facilities - authorisations | Sep 22 |  |  | Active participation in Brain Awareness Week campaign 2022 | May 22
Progress Report | Jun 22 |  |  | Ethics report | Feb 22 |  |  |  | 
Potential inputs for policy feedback | May 25 |  |  | Ethics report | May 23 |  |  |  | 
 |  |  |  | Ethics report | May 25 |  |  |  | 
Continuous Reporting - Deliverables

## Slide 11
WP1 Management |  | WP2 ESR Development |  | WP3 Ethics |  | WP 4-7 Research Objectives |  | WP8 Dissemination | 
Supervisory Board reps | Jul 21 | Career Development Plan for each ESR | Jun 22 | Humans – informed consent | Oct 21 | Presentation at international conference | May 24 | Establish CEN identity (logo, templates etc.) | Jul 21
Consortium Agreement | Nov 21 | Joint review article by ESRs | Nov 22 | Data processing | Oct 21 | Develop manuscripts for submission | May 25 | Establish website | Aug 21
Advertisements of ESR posts | Aug 21 | Mini symposium proposal submitted to SFN 2022 | May 23 | Animals - authorisations | Sep 22 |  |  | Press releases for CEN | Jul 21
Data Manage-ment Plan | Nov 21 | Publication for a lay readership | May 23 | Facilities - authorisations | Sep 22 |  |  | Active participation in Brain Awareness Week campaign 2022 | May 22
Progress Report | Jun 22 |  |  | Ethics report | Feb 22 |  |  |  | 
Potential inputs for policy feedback | May 25 |  |  | Ethics report | May 23 |  |  |  | 
 |  |  |  | Ethics report | May 25 |  |  |  | 
Continuous Reporting – Deliverables

## Slide 12
Continuous Reporting – Milestones
Title | Deliverable description / milestone means of verification | Month | Due date
Inauguration of Boards, Committees and Teams | Release of inaugural meeting minutes | 7 | 31 December 2021
Recruitment of ESRs completed | ESR contracts in place across all beneficiaries | 12 | 31 May 2022
All recruited fellows enrolledin PhD programme | Recruited ESRs enrolled | 12 | 31 May 2022
Experimental set-ups established including calcium imaging, viral tracing and fMRI studies | Reports of ESRs | 13 | 30 June 2022
Project Check | Meeting between REA and Consortium | 15 | 31 August 2022
Pilot data acquired | Reports of ESRs | 18 | 30 November 2022
Behavioural data sent to Pavia for computational modelling | Reports of ESRs | 24 | 31 May 2023
Secondments (minimum of 15 months) | Secondments in place, report of ESRs | 24 | 31 May 2023
Secondments (minimum of 30 months) | Secondments completed, reports of ESRs | 48 | 31 May 2025

## Slide 13
Website

## Slide 14
Training and development
Relationships in host labs
Alignment with local PhD programmes
Host training courses
Involvement in ethics proposals or undergraduate teaching
through local institutional networks
Network Meetings
Workshops
Webinars
Dissemination activities
Partner training sessions
through whole network teaching
Co-supervision
Mentoring
Secondments
Partner training sessions
interwoven networks between ESR projects involved within and across WPs

## Slide 15
Training and development
ESRs and Supervisors
Development Team
Supervisory Board
ESR Committee

## Slide 16
Training and development
ESRs and Supervisors
Development Team
Supervisory Board
ESR Committee
Two supervisors, two senior postdocs and two ESRs (from different institutions) and two representatives from non-academic partners.